## Sheet1
Category | Module | Tasks Required | Person in charge | Priority | Status
Website | SevenSprings | SevenSprings Website to have landing pages for purple bureau and for software development |  | 1
Website | SevenSprings | add a request button for partnership on the purplebureau page |  | 1
Website | SevenSprings | Adjust the landing pages to include text before the edits to encourage people to write something |  | 1
Youtube channel | SevenSprings | add the channel and add Purplebuerau video, the new one | Inas | 1
Graphics |  | Corporate identity of PurpleBureau. Taking into consieration the blue color more than the purple color | Israa | 2
Graphics |  | Corporate identity of PurpleBureau with the Atomic design feature | Israa | 2
PB development | GPS global | Add an option to use tracking GPS on the comapany level. (check boxes) 1- one option for using GPS tracking in sign-in and sign out. 2- a second option ot use the GPS in clients visits |  | 2
PB Development | CRM | Adjsut the date to contain year in activities |  | 1 | Done
Android | Expenses | Adjust the expenses OCR Bug to take into consideration the bug related to discount or returned value. |  | 1 | Ibrahim will start this sprint
PB Development | CRM | Adjust the detailed table to have attachement related to clients and not opportunities only. So we need to have attachment |  | 2 | Done
PB development | Backend Views | Adapt the responsiveness of the backend to be good on ipad and mobile. | Ruby on rails team | 2 | Alaa will start this sprint
PB development | Backend Views | adjust the view layout to be like the definition of the Requests. | Ruby on rails team | 1 | Esraa working on
Outlook development | CRM and Calendar | Update the outlook plugin to be able to add only the client and not to be forced to add the opportunity. It can be added as a step. Chose the client then. Are you sure that you want to add an opportunity? |  | 2
Management | Checklist | Create a check list for Backend and mobile application | Rana and Rasha | 1
Android | AR | Augmented reality task for sevensprings on Android. Exactly like we did in iOS and we will add an extra photo for the city of Description Antwerp for tourism example. From second 17th in the link https://www.youtube.com/watch?v=GAVaBQHFnP4 for 45 seconds masalan |  | 1 | Done
iOS | AR | add a video in sevensprings augmented reality movies From second 17th in the link https://www.youtube.com/watch?v=GAVaBQHFnP4 for 45 seconds masalan |  |  | Done
iOS | AR | Fix the bug of the business card which shows Kurt information on Omar and Embisa cards | Jimmy | 1
PB development | Performance | Evaluation module which we made the design should be put into action. We need to implement the evaluation module but we will need to add the name of the employee + the grade out of 5 + the dimension in relation to that in the appraisal module (it will be a lookup). so we can say, employee Ahmed, got 5 points, text: he said that he can do the task and he did the task in 2 hours instead of 4 hours and came and informed us, dimension: Yes i can attitude. the current design is missing this attitude. | Inas | 1 | done (API and listing BE) waiting ios & android & BE creation
PB development | Performance | on company level, show evaluation of manager to subordinate? And another show subordinate evaulation to Manager. Yes or no. When the evaluation is done from a subordinate towards his direct line manager, in this case only HR can see it. | Inas | 2 | done using BE settings
Graphics |  | design for the evaluation of employee and a screen for the employee to see every superior or colleague and how did he or she evaluate him. |  | 2 | done
PB Development | Recruitment | missing currency in the expected salary |  | 3
PB development | CRM | in Sales report, have a button showing last week |  | 3
PB development | CRM | when clicking on a certain line for a certain person, it should show me this person detailed entries. So if Mariana did enter 9 leads then when clicking on the cell of leads, it should open a page with the 9 leads. If I click on the cell of activities, then it should display the activities |  | 3
PB development | Clients Visits | backend APIs adjustments |  | 1 | done
Android | Clients Visits | Fix bugs |  | 1
iOS | Clients Visits | Fix bugs |  | 1 | under development
PB development | Notifications | Adjsut the messages of all the notification as they are not understandable
PB development | Voting | Adjust the disactivated employees bug |  |  | done
iOS | Voting | Design and stars and overall checking | needs refactor | 1
PB development | Voting | Save the voting results on the database not to retrieve it each time |  |  | done
PB development | Recruitment | finsih the interview cycle and the grading issue |  | 1
Android | Recruitment | finsih the interview cycle |  | 2
iOS | Recruitment | finsih the interview cycle |  | 2
PB development | Requests | Some Managers should be exempted from the approvals of their vacation. And the rule is on the request definition. So I know that Amadeus had this request and it was applied but I don’t find it and we discussed that it should be developed. |  | 1
PB development | Backups | Access the servers and make sure that all backups are taken properly. | IT and team leaders | 1
PB development | Backups | take one of the backups and restore it on an independent machine to make sure that everything is working | IT and Ruby on Rails team | 1
PHP and Wordpress | Training | Ibrahim should take a training on how wordpress functions and how PHP laravel functions | Ibrahim | 1
Alfresco | Documentation | All tips and tricks should be well documented. | Everybody | 1
PB development | View mode template | check few templates to see if we can change and make the view nicer. Currently we are using the gitlab template and it was updated but we didn't take the new update yet. | Ruby on rails team | 2
PB development | integration | Interface with office 365 on calendars | Ruby on rails team | 3
PB development | Attachment | get the files from different sources . Check how trello is doing it. | Ruby on rails team | 4
PB Development | CRM | Add the total activities done during a certain period in the sales report as a new summation | Ruby on rails team | 1 | done